## Team Story Assignments
Story ID | Story | Task | Teammate | Assigned Date | Status | Evidence
ST-01 | Payment domain models | Implement Payment and PaymentHistory entities | Chakrika Sai | 2026-07-30 | Completed | PR #1, PR #2
ST-02 | Account schema and JPA | Create account table schema and repository setup | KVS Ganesh | 2026-07-31 | Completed | Commits df81852, 1c57902
ST-03 | Payment endpoints | Build create/get payment APIs | Rachit Goyal | 2026-07-31 | Completed | Commit 73685f9, PR #5
ST-04 | Unit testing | Add backend unit test coverage | Hamsa Suresh | 2026-07-31 | Completed | Commit 0bbdc5e, PR #9
ST-05 | Exception handling | Implement global exception handling and mapping | Chakrika Sai | 2026-07-31 | Completed | Commit 8820d8a, PR #8
ST-06 | Input validations | Add request and business validations | KVS Ganesh | 2026-07-31 | Completed | Commit cbd67d0, PR #10
ST-07 | Client UI and API hooks | Create UI pages and integrate API calls | Rachit Goyal | 2026-08-01 | Completed | Commits b6a901d, 75938c0
ST-08 | OTP verification | Set up email OTP verification flow | Rachit Goyal | 2026-08-04 | Completed | Commit 4ea730a
ST-09 | CI/CD pipeline | Configure GitHub Actions and DB test service | Chakrika Sai | 2026-08-04 | Completed | Commits a0b2625, 2e99047
ST-10 | Dashboard and spend tracking | Add account dashboard and spending limit view | Rachit Goyal | 2026-08-04 | Completed | Commit 62150b9, PR #17
ST-11 | Status and balance updates | Add controllers for status change and balance updates | KVS Ganesh | 2026-08-04 | Completed | PR #14, PR #16
ST-12 | Lifecycle and integration fixes | Finalize payment lifecycle and frontend integration | Rachit Goyal | 2026-08-04 | Completed | Commits 060e2d7, cbf0cad
ST-13 | Sprint updates and tracker maintenance | Maintain development updates and task tracker documents | Chakrika Sai | 2026-08-05 | Completed | Commit 2ecbd92, 2fe3be0, d976421, PR #23
ST-14 | CD setup iteration | Implement and refine CD setup flow | Rachit Goyal | 2026-08-05 | Completed | Commits c4b2b8f, 84139cc, PR #24, PR #25
ST-15 | Pipeline hardening | Stabilize Jenkins/CD pipeline with test runs and fixes | Hamsa Suresh | 2026-08-06 | Completed | Commits 39ca9d4, 504cc25, 3f0ac4e, 6ecddd9, PR #26, PR #27
ST-16 | Client release merge | Integrate client branch and align repository docs | KVS Ganesh | 2026-08-06 | Completed | Commit f7a8745, PR #28
ST-17 | Client and CI fixes | Merge client updates and fix Jenkins/UI issues | Rachit Goyal | 2026-08-06 | Completed | Commits b4e09c7, ba9a85c, PR #29

## Commit and PR Tracker
Date | Type | Ref | Teammate | Title | Mapped Story | Status | PR # | Remarks
2026-08-06 | PR Merge | fdc9cdf | Chakrika Sai | Merge pull request #29 from Neueda-Learning/feat/client | Dashboard and Client UI | Completed | 29 | Merged branch: Neueda-Learning/feat/client
2026-08-06 | Commit | ba9a85c | Rachit Goyal | fix for jenkin | CI/CD Pipeline | Completed |  | Delivered in repository history
2026-08-06 | Commit | b4e09c7 | Rachit Goyal | fix: UI enhacements | Dashboard and Client UI | Completed |  | Delivered in repository history
2026-08-06 | PR Merge | ec0a8f3 | Hamsa Suresh | Merge pull request #28 from Neueda-Learning/feat/client | Dashboard and Client UI | Completed | 28 | Merged branch: Neueda-Learning/feat/client
2026-08-06 | Commit | f7a8745 | KVS Ganesh | added a root readme file | Documentation and Tracking | Completed |  | Delivered in repository history
2026-08-06 | Commit | 6ecddd9 | Hamsa Suresh | fix: jenkin pipeline | CI/CD Pipeline | Completed |  | Delivered in repository history
2026-08-06 | PR Merge | 024b4f4 | Hamsa Suresh | Merge pull request #27 from Neueda-Learning/feat/cd | General Engineering | Completed | 27 | Merged branch: Neueda-Learning/feat/cd
2026-08-06 | Commit | 3f0ac4e | Hamsa Suresh | fix: jenkin pipeline fixs | CI/CD Pipeline | Completed |  | Delivered in repository history
2026-08-06 | PR Merge | 6381671 | KVS Ganesh | Merge pull request #26 from Neueda-Learning/cd-test | General Engineering | Completed | 26 | Merged branch: Neueda-Learning/cd-test
2026-08-06 | Commit | 504cc25 | Hamsa Suresh | Trigger CI/CD test | CI/CD Pipeline | Completed |  | Delivered in repository history
2026-08-05 | PR Merge | 943edac | Rachit Goyal | Merge pull request #25 from Neueda-Learning/feat/cd | General Engineering | Completed | 25 | Merged branch: Neueda-Learning/feat/cd
2026-08-05 | Commit | 84139cc | Rachit Goyal | fix: cd setup fix | CI/CD Pipeline | Completed |  | Delivered in repository history
2026-08-05 | PR Merge | 47af7d5 | Rachit Goyal | Merge pull request #24 from Neueda-Learning/feat/cd | General Engineering | Completed | 24 | Merged branch: Neueda-Learning/feat/cd
2026-08-05 | Commit | c4b2b8f | Rachit Goyal | cd setup | CI/CD Pipeline | Completed |  | Delivered in repository history
2026-08-05 | Commit | 151242a | Rachit Goyal | Merge branch 'main' of https://github.com/Neueda-Learning/BugHunters_Payment_Processing into feat/cd | Payment and Account APIs | Completed |  | Delivered in repository history
2026-08-05 | PR Merge | 4f81a37 | Rachit Goyal | Merge pull request #23 from Neueda-Learning/feature/add-docs | Documentation and Tracking | Completed | 23 | Merged branch: Neueda-Learning/feature/add-docs
2026-08-05 | Commit | 2fe3be0 | Chakrika Sai | Added Task tracker. | Documentation and Tracking | Completed |  | Delivered in repository history
2026-08-05 | Commit | e0393af | Rachit Goyal | Merge branch 'main' of https://github.com/Neueda-Learning/BugHunters_Payment_Processing into feat/email | OTP Verification | Completed |  | Delivered in repository history
2026-08-05 | PR Merge | 017e487 | Chakrika Sai | Merge pull request #22 from Neueda-Learning/feat/dashboard | Dashboard and Client UI | Completed | 22 | Merged branch: Neueda-Learning/feat/dashboard
2026-08-05 | Commit | 1a153dc | Rachit Goyal | refactor: UI enhacement | Dashboard and Client UI | Completed |  | Delivered in repository history
2026-08-05 | PR Merge | d6ffb93 | Chakrika Sai | Merge pull request #19 from Neueda-Learning/feat/email | OTP Verification | Completed | 19 | Merged branch: Neueda-Learning/feat/email
2026-08-05 | PR Merge | e67c884 | KVS Ganesh | Merge pull request #21 from Neueda-Learning/setup-cd-pipeline | CI/CD Pipeline | Completed | 21 | Merged branch: Neueda-Learning/setup-cd-pipeline
2026-08-05 | Commit | e0a4c41 | Hamsa Suresh | modified cd setup | CI/CD Pipeline | Completed |  | Delivered in repository history
2026-08-05 | Commit | 0240cab | Rachit Goyal | Merge branch 'main' of https://github.com/Neueda-Learning/BugHunters_Payment_Processing into feat/email | OTP Verification | Completed |  | Delivered in repository history
2026-08-05 | Commit | d976421 | Chakrika Sai | Update date in development updates document | Documentation and Tracking | Completed |  | Delivered in repository history
2026-08-05 | PR Merge | 2a1c14d | KVS Ganesh | Merge pull request #20 from Neueda-Learning/feature/cd-setup | General Engineering | Completed | 20 | Merged branch: Neueda-Learning/feature/cd-setup
2026-08-05 | Commit | 39ca9d4 | Hamsa Suresh | Created cd setup | CI/CD Pipeline | Completed |  | Delivered in repository history
2026-08-05 | Commit | f81ba92 | Rachit Goyal | refactor: dashboard enhacement | Dashboard and Client UI | Completed |  | Delivered in repository history
2026-08-05 | Commit | f0999f8 | Rachit Goyal | Align the test case according to correct lifecycle | Integration and Payment Lifecycle | Completed |  | Delivered in repository history
2026-08-04 | Commit | cbf0cad | Rachit Goyal | fix: frontend integration with corrected lifecycle | Integration and Payment Lifecycle | Completed |  | Delivered in repository history
2026-08-04 | Commit | 060e2d7 | Rachit Goyal | fix: payment lifecycle fix | Integration and Payment Lifecycle | Completed |  | Delivered in repository history
2026-08-04 | Commit | 4ea730a | Rachit Goyal | OTP setup and integration done | OTP Verification | Completed |  | Delivered in repository history
2026-08-04 | PR Merge | 370b7ce | Hamsa Suresh | Merge pull request #15 from Neueda-Learning/feature/ci-setup | CI/CD Pipeline | Completed | 15 | Merged branch: Neueda-Learning/feature/ci-setup
2026-08-04 | Commit | 7a2e352 | Chakrika Sai | Merge branch 'main' into feature/ci-setup | CI/CD Pipeline | Completed |  | Delivered in repository history
2026-08-04 | Commit | 2e99047 | Chakrika Sai | Configure CI with MySQL service instead of H2 | CI/CD Pipeline | Completed |  | Delivered in repository history
2026-08-04 | PR Merge | 64df6a2 | Hamsa Suresh | Merge pull request #17 from Neueda-Learning/feat/dashboard | Dashboard and Spending Insights | Completed | 17 | Merged branch: Neueda-Learning/feat/dashboard
2026-08-04 | Commit | 335ddff | Rachit Goyal | Merge branch 'main' of https://github.com/Neueda-Learning/BugHunters_Payment_Processing into feat/dashboard | Dashboard and Spending Insights | Completed |  | Delivered in repository history
2026-08-04 | PR Merge | 1113580 | KVS Ganesh | Merge pull request #16 from Neueda-Learning/feat/change_status | Status and Balance Updates | Completed | 16 | Merged branch: Neueda-Learning/feat/change_status
2026-08-04 | Commit | fee286c | Hamsa Suresh | controller to change status of the payment | Payment and Account APIs | Completed |  | Delivered in repository history
2026-08-04 | Commit | c85bf52 | Chakrika Sai | Fix backend CI database test configuration | CI/CD Pipeline | Completed |  | Delivered in repository history
2026-08-04 | Commit | bfd5106 | Chakrika Sai | Merge branch 'main' into feature/ci-setup | CI/CD Pipeline | Completed |  | Delivered in repository history
2026-08-04 | Commit | a0b2625 | Chakrika Sai | Added GitHub Actions CI pipeline | CI/CD Pipeline | Completed |  | Delivered in repository history
2026-08-04 | PR Merge | 49d7379 | Rachit Goyal | Merge pull request #14 from Neueda-Learning/feat/upd_bal | General Engineering | Completed | 14 | Merged branch: Neueda-Learning/feat/upd_bal
2026-08-04 | Commit | 62150b9 | Rachit Goyal | Added the dashboard to track spending limit | Dashboard and Spending Insights | Completed |  | Delivered in repository history
2026-08-04 | Commit | 5a03db3 | KVS Ganesh | Merge branch 'main' of https://github.com/Neueda-Learning/114_BugHunters into feat/upd_bal | General Engineering | Completed |  | Delivered in repository history
2026-08-04 | Commit | d199ed4 | KVS Ganesh | added some controllers | Payment and Account APIs | Completed |  | Delivered in repository history
2026-08-04 | PR Merge | e2f65f3 | Chakrika Sai | Merge pull request #13 from Neueda-Learning/fix | General Engineering | Completed | 13 | Merged branch: Neueda-Learning/fix
2026-08-04 | Commit | e038361 | Rachit Goyal | Merge branch 'main' of https://github.com/Neueda-Learning/BugHunters_Payment_Processing into fix | General Engineering | Completed |  | Delivered in repository history
2026-08-04 | Commit | 287a48e | Chakrika Sai | Merge branch 'main' of https://github.com/Neueda-Learning/BugHunters_Payment_Processing | General Engineering | Completed |  | Delivered in repository history
2026-08-04 | Commit | 2ecbd92 | Chakrika Sai | Added project development updates documentation | Documentation | Completed |  | Delivered in repository history
2026-08-04 | Commit | abb61b6 | Rachit Goyal | integration fix | Integration and Payment Lifecycle | Completed |  | Delivered in repository history
2026-08-04 | PR Merge | 3f940b9 | Chakrika Sai | Merge pull request #11 from Neueda-Learning/fix | General Engineering | Completed | 11 | Merged branch: Neueda-Learning/fix
2026-08-04 | Commit | fe3b8f4 | Rachit Goyal | Merge branch 'main' of https://github.com/Neueda-Learning/BugHunters_Payment_Processing into fix | General Engineering | Completed |  | Delivered in repository history
2026-08-04 | PR Merge | 0c67109 | Chakrika Sai | Merge pull request #10 from Neueda-Learning/feat/valid | General Engineering | Completed | 10 | Merged branch: Neueda-Learning/feat/valid
2026-08-03 | Commit | cbd67d0 | KVS Ganesh | Adding the validations part | Input Validation | Completed |  | Delivered in repository history
2026-08-03 | Commit | 1ae4243 | Rachit Goyal | Merge branch 'main' of https://github.com/Neueda-Learning/BugHunters_Payment_Processing into fix | General Engineering | Completed |  | Delivered in repository history
2026-08-03 | PR Merge | 5433137 | Rachit Goyal | Merge pull request #9 from Neueda-Learning/feat/test | Testing | Completed | 9 | Merged branch: Neueda-Learning/feat/test
2026-08-03 | Commit | 6370222 | Rachit Goyal | fix: key generated on server side | General Engineering | Completed |  | Delivered in repository history
2026-08-03 | PR Merge | 3354d99 | Rachit Goyal | Merge pull request #8 from Neueda-Learning/feat/exception | Exception Handling | Completed | 8 | Merged branch: Neueda-Learning/feat/exception
2026-08-03 | Commit | 581f819 | Rachit Goyal | fix: correcting the error code as per the description | General Engineering | Completed |  | Delivered in repository history
2026-08-03 | PR Merge | 612f5e8 | Rachit Goyal | Merge pull request #6 from Neueda-Learning/feature/exception | Exception Handling | Completed | 6 | Merged branch: Neueda-Learning/feature/exception
2026-08-03 | PR Merge | 6ede01b | Rachit Goyal | Merge pull request #7 from Neueda-Learning/feat/client | General Engineering | Completed | 7 | Merged branch: Neueda-Learning/feat/client
2026-08-01 | Commit | 75938c0 | Rachit Goyal | defining function to call apis | Payment and Account APIs | Completed |  | Delivered in repository history
2026-08-01 | Commit | b6a901d | Rachit Goyal | Basic UI pages | General Engineering | Completed |  | Delivered in repository history
2026-07-31 | Commit | 0bbdc5e | Hamsa Suresh | added unit testing part | Testing | Completed |  | Delivered in repository history
2026-07-31 | Commit | 05ab7e0 | KVS Ganesh | Added Validations | Input Validation | Completed |  | Delivered in repository history
2026-07-31 | Commit | 8820d8a | Chakrika Sai | Exception folder created | Exception Handling | Completed |  | Delivered in repository history
2026-07-31 | Commit | ab7d051 | KVS Ganesh | Added JPA extension for Account table | Account Schema and JPA | Completed |  | Delivered in repository history
2026-07-31 | Commit | 1c57902 | KVS Ganesh | Added Account table | Account Schema and JPA | Completed |  | Delivered in repository history
2026-07-31 | PR Merge | 520a481 | Chakrika Sai | WIP on main: 07ac5a8 Merge pull request #3 from Neueda-Learning/feat/schema | Account Schema and JPA | In Progress | 3 | Work in progress marker
2026-07-31 | PR Merge | 2badb0a | Chakrika Sai | index on main: 07ac5a8 Merge pull request #3 from Neueda-Learning/feat/schema | Account Schema and JPA | Completed | 3 | Merged branch: Neueda-Learning/feat/schema
2026-07-31 | PR Merge | 0ec65bd | Chakrika Sai | untracked files on main: 07ac5a8 Merge pull request #3 from Neueda-Learning/feat/schema | Account Schema and JPA | Completed | 3 | Merged branch: Neueda-Learning/feat/schema
2026-07-31 | Commit | ffcfbb3 | KVS Ganesh | newly added the account table | Account Schema and JPA | Completed |  | Delivered in repository history
2026-07-31 | Commit | e774acc | KVS Ganesh | newly added the account table | Account Schema and JPA | Completed |  | Delivered in repository history
2026-07-31 | PR Merge | 7788615 | Rachit Goyal | Merge pull request #5 from Neueda-Learning/feat/endpoints | Payment and Account APIs | Completed | 5 | Merged branch: Neueda-Learning/feat/endpoints
2026-07-31 | Commit | 39fa8de | Hamsa Suresh | Created some more endpoints | Payment and Account APIs | Completed |  | Delivered in repository history
2026-07-31 | PR Merge | e53f235 | Chakrika Sai | Merge pull request #4 from Neueda-Learning/feat/endpoints | Payment and Account APIs | Completed | 4 | Merged branch: Neueda-Learning/feat/endpoints
2026-07-31 | Commit | 73685f9 | Rachit Goyal | Created endpoint to create and get payment details | Payment and Account APIs | Completed |  | Delivered in repository history
2026-07-31 | PR Merge | 07ac5a8 | Rachit Goyal | Merge pull request #3 from Neueda-Learning/feat/schema | Account Schema and JPA | Completed | 3 | Merged branch: Neueda-Learning/feat/schema
2026-07-31 | Commit | df81852 | KVS Ganesh | created table in db and schema attached for reference | Account Schema and JPA | Completed |  | Delivered in repository history
2026-07-31 | PR Merge | 0f0d8b7 | Chakrika Sai | Merge pull request #2 from Neueda-Learning/feature/payment-models | General Engineering | Completed | 2 | Merged branch: Neueda-Learning/feature/payment-models
2026-07-30 | Commit | 7e4e521 | Rachit Goyal | Changed datatype of status from String to enum | Payment Models | Completed |  | Delivered in repository history
2026-07-30 | Commit | 8a2f299 | Rachit Goyal | Added JPA annotation to the tables | Account Schema and JPA | Completed |  | Delivered in repository history
2026-07-30 | PR Merge | 0c4c766 | Rachit Goyal | Merge pull request #1 from Neueda-Learning/feature/payment-models | General Engineering | Completed | 1 | Merged branch: Neueda-Learning/feature/payment-models
2026-07-30 | Commit | ef6ea7f | Chakrika Sai | Added Payment and PaymentHistory models | Payment Models | Completed |  | Delivered in repository history
2026-07-30 | Commit | 06d75ea | Rachit Goyal | Initial commit | General Engineering | Completed |  | Delivered in repository history

## Summary
Metric | Value | Notes
Total Stories | 17 | Story entries in assignment sheet
Completed Stories | 17 | Based on status column
In Progress Stories | 0 | Based on status column
Stories Needing Review | 0 | Health marked as Needs Review
PR Merges Logged | 30 | Detected from merge commit subjects
Total History Entries | 86 | Commits and merges collected from git log --all
Generated On | 2026-08-06 | Tracker generated automatically
Contributor | Entries | Activity Mix
Chakrika Sai | 22 | PR merges: 11
Hamsa Suresh | 12 | PR merges: 4
KVS Ganesh | 14 | PR merges: 4
Rachit Goyal | 38 | PR merges: 11